## Change Request 1
Group members: | Abdullah Moyeen
Mahabubul Alam
Software system: | jEdit
Change Request #1 | Modify the search function of the recent files list so that the matching occurs when the string is contained anywhwere in the file name.
Modified classes: | org/gjt/sp/jedit/menu/RecentFilesProvider.java
Time spent on this change request: | 85 mins
Initiation | 30 mins
Concept location | 30 mins
Impact analysis | 15 mins
Actualization | 5 mins
Testing | 5 mins
Process followed to implement the Change Request:
Initiation | 1. Ran the Jedit project as a Java Application.
2. Opened the "Recent File" menu
3. We will search for "Recent Files" for usage
Concept location | 1. Search for "Recent Files" for usage | `
2. jedit_gui.props shows call to RecentFileProvider()
3. Seach for RecentFileProvider
…
We will modify the update(Jmenu) method in the RecentFilesProvider class
Impact analysis | 1. Marked the RecentFilesProvider class as impacted, because the update(Jmenu) method will be modified.
…
N. The impact set is … RecentFilesProvider
Actualization | 1. Changed the update(Jmenu) method by replacing startsWith(typedText.toLowerCase()) with contains(typeText.toLowerCase())
Testing | 1. Opened several Files to populate the recent file list.
2. Tested by starting to type a letter that does not start any of the file names.
3. Tested by starting to type a letter that starts one or some of the file name(s).
Additional information
Class Diagram for each phase is in /docs/images folder in the repo

## Change Request 2
Group members: | Abdullah Moyeen
Mahabubul Alam
Software system: | jEdit
Change Request #2 | Implement an option in the jEdit menu which when clicked, allows hiding the scrollbars
Modified classes: | org/gjt/sp/jedit/textarea/TextArea.java
Time spent on this change request: | 325 mins
Initiation | 30 mins
Concept location | 200 mins
Impact analysis | 50 mins
Actualization | 35 mins
Testing | 10 mins
Process followed to implement the Change Request:
Initiation | 1. Ran the Jedit project as a Java Application.
2. Opened Text File, Both Scrollbars are visible.
3. We will search for "More Selection" for usage since it has similar behavior in menu to what is asked in CR2
Concept location | 1. Search for "More Selection" for usage | `
2. jedit_gui.props are creating the menus
3. Search to identify where scrollbars are created
4. Search to identify and replicate the "Toggle Gutter" menu item behavior
5. Search to identify the TextArea class where we can add methods to modify scrollbar visibility
6. Following the gutter seemed to be useless, actions.xml gave us better clue
…
We will modify TextArea.java, actions.xml and jedit_gui.props
Impact analysis | 1. Marked the TextArea class as imapcted, because this is where we need a method to control the visibility of the scrollbars.
2. The actions.xml file is marked as impacted, because this here we set the behavior of the menu item
3. The jedit_gui.props files is marked as impacted, because this is where we will add the menu items.
…
N. The impact set is … TextArea, actions.xml, jedit_gui.props
Actualization | 1. In jedit_gui.props added Toggle Scrollbars menu item with submeny items for togglilng the Horizontal and Vertical Scrollbars
2. In actions.xml added actions "toggle-vertical" and "toggle-horizontal"
3. In TextArea class, added methods toggleVerticalScrollbar() and toggleHorizontalScrollbar()
Testing | 1. Tested Vertical Scrollbar toggling by using the sub-menu item added under Edit->Toggle Scrollbars
2. Tested Horizontal Scrollbar toggling by using the sub-menu item added under Edit->Toggle Scrollbars
3. Testd the Other menu items under "Edit" menu to make sure nothing broke adter our changes were committed.
Additional information
Class Diagram for each phase is in /docs/images folder in the repo