## Change Request 1
Group members: | Abdullah Moyeen
Mahabubul Alam
Software system: | jEdit
Change Request #1 | Modify the search function of the recent files list so that the matching occurs when the string is contained anywhwere in the file name.
Modified classes: | org/gjt/sp/jedit/menu/RecentFilesProvider.java
Time spent on this change request: | 85 mins
Initiation | 30 mins
Concept location | 30 mins
Impact analysis | 15 mins
Actualization | 5 mins
Testing | 5 mins
Process followed to implement the Change Request:
Initiation | 1. Ran the Jedit project as a Java Application.
2. Opened the "Recent File" menu
3. We will search for "Recent Files" for usage
Concept location | 1. Search for "Recent Files" for usage | `
2. jedit_gui.props shows call to RecentFileProvider()
3. Seach for RecentFileProvider
…
We will modify the update(Jmenu) method in the RecentFilesProvider class
Impact analysis | 1. Marked the RecentFilesProvider class as impacted, because the update(Jmenu) method will be modified.
…
N. The impact set is … RecentFilesProvider
Actualization | 1. Changed the update(Jmenu) method by replacing startsWith(typedText.toLowerCase()) with contains(typeText.toLowerCase())
Testing | 1. Opened several Files to populate the recent file list.
2. Tested by starting to type a letter that does not start any of the file names.
3. Tested by starting to type a letter that starts one or some of the file name(s).
Additional information
Class Diagram for each phase is in /docs/images folder in the repo

## Change Request 2
Group members: | Abdullah Moyeen
Mahabubul Alam
Software system: | jEdit
Change Request #2 | Implement an option in the jEdit menu which when clicked, allows hiding the scrollbars
Modified classes: | org/gjt/sp/jedit/textarea/TextArea.java
315 mins
Time spent on this change request:
Initiation | 10 mins
Concept location | 200 mins
Impact analysis | 50 mins
Actualization | 35 mins
Testing | 10 mins
Process followed to implement the Change Request:
Initiation | 1. Ran the Jedit project as a Java Application.
2. Opened Text File, Both Scrollbars are visible.
3. We will search for "More Selection" for usage since it has similar behavior in menu to what is asked in CR2
Concept location | 1. Search for "More Selection" for usage | `
2. jedit_gui.props are creating the menus
3. Search to identify where scrollbars are created
4. Search to identify and replicate the "Toggle Gutter" menu item behavior
5. Search to identify the TextArea class where we can add methods to modify scrollbar visibility
6. Following the gutter seemed to be useless, actions.xml gave us better clue
…
We will modify TextArea.java, actions.xml and jedit_gui.props
Impact analysis | 1. Marked the TextArea class as imapcted, because this is where we need a method to control the visibility of the scrollbars.
2. The actions.xml file is marked as impacted, because this here we set the behavior of the menu item
3. The jedit_gui.props files is marked as impacted, because this is where we will add the menu items.
…
N. The impact set is … TextArea, actions.xml, jedit_gui.props
Actualization | 1. In jedit_gui.props added Toggle Scrollbars menu item with submeny items for togglilng the Horizontal and Vertical Scrollbars
2. In actions.xml added actions "toggle-vertical" and "toggle-horizontal"
3. In TextArea class, added methods toggleVerticalScrollbar() and toggleHorizontalScrollbar()
Testing | 1. Tested Vertical Scrollbar toggling by using the sub-menu item added under Edit->Toggle Scrollbars
2. Tested Horizontal Scrollbar toggling by using the sub-menu item added under Edit->Toggle Scrollbars
3. Testd the Other menu items under "Edit" menu to make sure nothing broke after our changes were committed.
Additional information
Class Diagram for each phase is in /docs/images folder in the repo

## Change Request 3
Group members: | Abdullah Moyeen
Mahabubul Alam
Software system: | jEdit
Change Request #2 | Add "creation date" to the list of columns in edit favorites window jEdit and implement sorting by creation date
Modified classes: | org/gjt/sp/jedit/browser/VFSDirectoryEntryTableModel.java
org/gjt/sp/jedit/io/FavoritesVFS.java
org/gjt/sp/jedit/io/VFSFile.java
Time spent on this change request: | 210 mins
Initiation | 10 mins
Concept location | 100 mins
Impact analysis | 30 mins
Actualization | 60 mins
Testing | 10 mins
Process followed to implement the Change Request:
Initiation | 1. Ran the Jedit project as a Java Application.
2. Opened Utilities->Favorites->Edit Favorites
3. We will search for "Edit Favorties" for usage
Concept location | 1. Search for "Edit Favorites" for usage | `
2. Usage Found in jedit_gui.props, actions.xml & VFSBrowser.java
3. Trying to get clue fom the browseDirectory & setDirectory methods in VFSBrowser class
4. Could not figure out how to get the values for path, decided to regroup after searching on stackexchange and reading the jEdit API
5. 3rd day, looks like the VFS Class is being initialized and passes extended atributes, we need an EA_CREATED attribute
6. We need to use java.nio.file to populate it and it requires path of the file
7. searched in FavoritesVFS - found a class and realzied that we will get the path from VFSFile.java and path is in the constructor
8. For sorting, did a global seach for EA_MODIFIED. It appears, VFSDirectoryEntryTableModel.java - has a sorting method, we will try to replicate that.
…
We will modify VFSDirectoryEntryTableModel.java, FavoritesVFS.java, VFSFile.java &
Impact analysis | 1. Marked the VFS.java files as impacted, because we will need an extended attribute here.
2. The VFSFile.java class is marked as impacted, because we will need a method to get the creation time here.
3. The VFSDirectoryEntryTableModel.java class is marked as impacted, since we will need to modify it for sorting using Date Created
4. The jedit_gui.props files is marked as impacted, because this is where we will add the menu items.
…
N. The impact set is … VFS.java, VFSFile.java, VFSDirectoryModel.java & jedit_gui.props
Actualization | 1. Added EA_CREATED extended attribute in VFS.java
2. Added getCreationTime method in VFSFile class.
3. In VFSDirectoryEntryTableModel.java, added a branch for EA_CREATED.
4. Added vfs.browser.created=Creation date in jedit_gui.props
Testing | 1. Tested new functionality by opening the edit favorites window and populating with multiples files.
2. Column Header "Date Created" is visible and sorting works.
3. Tested the Other menu items under "Edit Favorites" menu to make sure nothing broke after our changes were committed.
Additional information
Class Diagram for each phase is in /docs/images folder in the repo